## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2225-swen-261-01-c Vybes
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page. | Pass |  |  | AY
| Given that I am not on the Products page when I choose the Products page then I am taken to the Products page. | Pass
| Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available. | Pass
| Given that I am on the products page when there are products in the inventory then I see each product and short description. | Pass
| Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart. | Pass
As an admin, I want to be able to add new flavors from the website so that users can purchase the new flavors on the website. | Given anyone when a flavor is used then it should be based off of a saved json | Pass
| Given the admin when adding a flavor then the new flavor should be available to be added to new waters. | Pass
| Given the admin when removing a flavor then something should be done with any aquas with that flavor | Pass
As a user, I want to be able to see what is available so that I can decide what I want to buy. | given a user when they load the website then I want to be able to display the entire inventory | Pass
As an ADMIN, I want create Aquas on the website so that I do not have to make requests from command line. | Given a user is logged in as admin when they create a new aqua on the webpage then a new aqua is created and added to persistent data. | Pass
As a customer, I want to save the current shopping cart so that I store and later see which waters I wanted to buy, and compare all of the selected products. | Given a buyer when they sign out then their cart is saved. | Pass
As a USER, I want to search the inventory so that I can see what is available for purchase. | Given a user searching the store when a query is entered then products matching that query are displayed | Pass
| Given a query when a flavor or name is entered then products matching that criteria are displayed | Pass
As a buyer I want to be able to put my items in a shopping cart so that I can find an item I like, put it in my cart and continue shopping. | Given a buyer when the buyer adds an item to cart then the item is added to the cart. | Pass
| Given a buyer when the buyer removes an item from the cart then the item is removed from the cart. | Pass
| Given a buyer when the buyer leaves without checking out then the items are saved in the cart. | Pass
| Given a buyer when the buyer checks out then the items are checked out and a work order is created. | Pass
| Given an admin when they try to access their cart, nothing happens | Pass
As an admin, I want to login so that I can access administrative information. | Given admin username when logging in then user is known as admin and has access to admin specific features (Like editing flavors). | Pass
| Given username other than admin when logging in then user is a buyer and able to access the site regular. | Pass
As a user, I want to be able to register a username so that I can create an account and login to it afterwards. | given the login page when the user enters a username other than admin then the website logs them in as a user and loads their user file. | Pass
| given the login page when the user enters a new username then a new user is created in the backend | Pass
As a user, I want feedback so that I know when something happened | Given create aqua when add to cart button is clicked then it should notify the customer that the item was added | Pass
| Given cart when checkout button is clicked then it should notify the customer what there order was | Pass
| Given the website when the user is not signed in then it should bring them to the sign in page | Pass
As a USER, I want a description of a flavor so that I know what I am ordering. | Given a user is on the flavors page when they click on a flavor then a details component is brought up with a description of the flavor. | Pass
As an ADMIN, I want to be able to edit flavors so that changes in inventory or products are represented on the website. | Given a user is logged in as admin when they browse the flavors page then there is a button to edit each flavor. | Pass
| Given an admin is on the edit flavor page, when they submit their edits then whenever another user views the flavor on the flavors page or create aqua page, the changes are represented. | Fail | Alec B, 4/4/23, when I update the flavor with description and quantity, changes are not reflected in json file
As a user, I want the server to validate that there is enough inventory so that I can actually get what I want. | Given create aqua when the user selects pack size then it should verify that there is enough inventory | Fail | Andrew Y, 4/4/23, adds to cart even if there is no inventory
| Given checkout when the user checks out then it should verify that there is enough inventory before it sends the order | Pass
As a User, I want my cart to change when the flavors are updated so that I have the current information. | Given the cart when the a flavor is updated or removed then the cart is updated | Pass
| given the cart when there is a problem with something then the user should be given a ui notification that something has changed or is wrong | Pass
As a customer, I want to be able to create codes for my custom water so that I can share what I made | Given a custom water (Made in the create aqua screen) when the user clicks a generate code button then a new code is generated and shown to the user | Fail | Andrew P, 4/4/23, works except for "Load from Code" and "Get from code" buttons
As a user, I want to be able to recreate custom products from their unique product code so that I can order waters that I previously created or those that others created. | Given I have a product code when I enter it into the "load from code" form in the custom water page then a custom water corresponding to the entered code is generated. | Fail | Alec B, 4/4/23: Pressing "load from code" didn't update the fields.
As a Customer, I want to view previous orders so that I know what I’ve bought previously and how much it cost. | Given that a user is on the website when they are authenticated then there should be a button for viewing previous orders. | Fail | Alec B, 4/4/23: tried to view "past orders" after checking out and didn't find the previous item he bought.
| Given previous orders when a user clicks the "Previous orders" button then they are shown previous orders. | Pass
As a user, I want to be able to create a 6 pack with different custom flavors (like a dozen donuts box) so that I can have variety at a discount. | Given the user when when they click on the create your own pack route then it should bring them to that page | Pass
| Given the user when when they create a new aqua then it should be added to that pack | Pass
| Given the user when when they click on finish pack then it should add the pack to the cart | Pass
As a user, I want to have more features in the shopping cart so that the platform is easier to use. | Given a cart when a user checks out then the user should be able to increase the quantity of a bought product from the cart | Pass
| Given a cart when a user has multiple of the same product then the products should merge into one product with a quantity of the amount of the same product. | Pass
| Given a user when they checkout then the user should be able to see the price of their cart. | Pass
|  | Fail | Andrew Y, admin is able to add to a cart
|  | Fail | Alec B: Add notifications to cart
|  | Fail | Alec B: "Not enough stock" popup when removing items from cart
|  | Fail | Shopping cart doesn't clear after checking out
|  | Fail | Alec B: when I try to add a flavor with no quantity, it adds to cart and notification says it added to cart. Cannot remove from cart since 0 quantity
|  | Fail | Alec B: When switching to cart, create type enum
Email: arb5076@rit.edu